Table 1. Timeline of events.

|  |  |
| --- | --- |
| December 2019 | * Informal discussions began around forming CLABSI Rounding Team
 |
| February 2020 | * First meeting with initial core team members to discuss CLABSI Rounding Team process
 |
| March-May 2020 | * Initial COVID-19 response; CLABSI work put on hold
 |
| May-June 2020 | * Creation of standardized Microsoft Form audit tool
 |
| June 2020 | * CLABSI Rounding Team began bi-weekly meetings
* Oncology service line began CLABSI rounds on 2 units
 |
| July 2020 | * Met with Business Operations team to begin process of PowerBI dashboard build
* Surgical service line began CLABSI rounds on 2 units
* Creation of CLABSI Reduction Toolkit with supporting documents stored on a facility intranet webpage
 |
| August 2020 | * Two more surgical units started CLABSI rounds
* One more oncology unit started CLABSI rounds
 |
| September 2020 | * Medical unit started CLABSI rounds
* PowerBI dashboard went live
 |
| October 2020 | * Neurosciences service line began CLABSI rounds on one unit
 |
| November 2020 | * Cardiac service line began CLABSI rounds on one unit
 |
| December 2020 | * COVID-19 hospitalizations surge; CLABSI work slowed
* One more cardiac unit started CLABSI rounds
 |
| January 2021 | * Go-live of new products including chlorhexidine impregnated dressing and chlorhexidine swabs
 |
| March 2021 | * Presented work to the Vascular Access Team to promote awareness and collaboration
* One more medical unit started CLABSI rounds
* One more surgical unit started CLABSI rounds
* Expanded CLABSI rounds to include units without available CNS or CNL
 |
| March-April2021 | * Implementation of CLABSI attestation form and bedside shift report tool
 |
| April 2021 | * One more neurosciences unit started CLABSI rounds
 |
| May 2021 | * One more neurosciences unit started CLABSI rounds
 |
| July 2021 | * Completed survey to assess barrier to utilizing chlorhexidine swabs
 |
| July-October 2021 | * Completed ‘Scrub the Hub’ rounds to address inconsistencies in using chlorhexidine swabs
 |
| August 2021 | * COVID-19 hospitalizations surge; CLABSI works slowed
 |

-