Table 1. Timeline of events.

|  |  |
| --- | --- |
| December 2019 | * Informal discussions began around forming CLABSI Rounding Team |
| February 2020 | * First meeting with initial core team members to discuss CLABSI Rounding Team process |
| March-May 2020 | * Initial COVID-19 response; CLABSI work put on hold |
| May-June 2020 | * Creation of standardized Microsoft Form audit tool |
| June 2020 | * CLABSI Rounding Team began bi-weekly meetings * Oncology service line began CLABSI rounds on 2 units |
| July 2020 | * Met with Business Operations team to begin process of PowerBI dashboard build * Surgical service line began CLABSI rounds on 2 units * Creation of CLABSI Reduction Toolkit with supporting documents stored on a facility intranet webpage |
| August 2020 | * Two more surgical units started CLABSI rounds * One more oncology unit started CLABSI rounds |
| September 2020 | * Medical unit started CLABSI rounds * PowerBI dashboard went live |
| October 2020 | * Neurosciences service line began CLABSI rounds on one unit |
| November 2020 | * Cardiac service line began CLABSI rounds on one unit |
| December 2020 | * COVID-19 hospitalizations surge; CLABSI work slowed * One more cardiac unit started CLABSI rounds |
| January 2021 | * Go-live of new products including chlorhexidine impregnated dressing and chlorhexidine swabs |
| March 2021 | * Presented work to the Vascular Access Team to promote awareness and collaboration * One more medical unit started CLABSI rounds * One more surgical unit started CLABSI rounds * Expanded CLABSI rounds to include units without available CNS or CNL |
| March-April2021 | * Implementation of CLABSI attestation form and bedside shift report tool |
| April 2021 | * One more neurosciences unit started CLABSI rounds |
| May 2021 | * One more neurosciences unit started CLABSI rounds |
| July 2021 | * Completed survey to assess barrier to utilizing chlorhexidine swabs |
| July-October 2021 | * Completed ‘Scrub the Hub’ rounds to address inconsistencies in using chlorhexidine swabs |
| August 2021 | * COVID-19 hospitalizations surge; CLABSI works slowed |

-