**Supplementary Table 3.** Description of Implementation Strategies to be used for BHS+ORCHID Implementation

|  |  |
| --- | --- |
| Implementation Strategy as Operationalized for BHS+ORCHID | Corresponding ERIC strategy |
| We conducted surveys and interviews with MCMs on resources and needs for BHS and referral to ORCHID (BHS+ORCHID). Information about needs also comes from pilot results and current diagnoses in the electronic records.  | Conduct local needs assessmentAssess for readiness and identify barriers and facilitators |
| AFC and Research Partners will attend clinic and systemwide MCM and Supervisor meetings to share information about the BHS+ORCHID.  | Conduct educational meetings  |
| AFC and Research Partners will develop and distribute educational materials about BHS+ ORCHID to each site.  | Develop and distribute educational materials |
| AFC will hold pre-implementation and ongoing trainings on the BHS+ORCHID. Trainings will be in person and online and will use a variety of learning modalities (e.g., lecture, role play). Trainings will describe permitted variation in BHS+ORCHID implementation. | Conduct ongoing trainingMake training dynamicPromote adaptability |
| AFC and Research Partners will develop a formal implementation manual on: (1) purpose of implementing BHS+ORCHID, (2) scope of change at client, staff, and clinic levels, (3) timeframe and milestones, and (4) appropriate performance measures. | Develop a formal implementation blueprint |
| Research Partners will conduct ongoing surveys and focus groups to discuss implementation  | Capture and share local knowledgePurposefully reexamine the implementation processTailor and adapt strategies |
| AFC will provide local technical assistance on implementing the BHS within their existing electronic record system. Research partners will provide technical assistance on client referral to and use of ORCHID.  | Centralize technical assistance  |
| AFC and Research Partners will engage supervisors to receive feedback based on pilot process of BHS+ORCHID. individuals with positive experiences from the BHS pilot will be invited to trainings. | Identify and prepare champions |
| AFC will track all BHS data in a centralized electronic record system and provide a dashboard and regular reports to clinics. | Audit and provide feedback |
| AFC will develop a quality management system including specific follow-up plan and benchmarks, procedures, timelines, and general processes | Develop and implement tools for quality monitoring Develop and organize quality monitoring systems |

Abbreviations. BHS=Behavioral Health Survey; ORCHID=Optimizing Resilience and Coping with HIV through Internet Delivery